## Description
Scenario Quality Checker (SQC)
For analysts documenting functional requirements with scenarios, our SQC application will provide quantitative information and enable detection of problems in functional requirements written in the form of scenarios. The application will be available via GUI and also as a remote API, thanks to which it can be integrated with existing tools.
Format of scenarios to be put into the Readme.md project: • The scenario includes a header specifying its title and actors (external and system) • The scenario consists of steps (each step contains text) • Steps can contain sub-scenarios (any level of nesting) • The steps may start with the keywords IF, ELSE, FOR EACH Example: Title: Book addition Actors: Librarian System actor: System • Librarian selects options to add a new book item • A form is displayed. • Librarian provides the details of the book. • IF: Librarian wishes to add copies of the book o Librarian chooses to define instances o System presents defined instances o FOR EACH: instance: • Librarian chooses to add an instance • System prompts to enter the instance details • Librarian enters the instance details and confirms them. • System informs about the correct addition of an instance and presents the updated list of instances. • Librarian confirms book addition. • System informs about the correct addition of the book.

## Product Backlog
Product Backlog item | Importance | Labour intensity | Business Value (BV) | Acceptance Criteria
As a developer of analyst tools, I can use the available functions remotely via REST to be able to integrate the tool with my other applications | 20 | 6 | 1 | o Input in JSON format corresponding to the structure of a scenario (dictionaries, lists) o Input transformed into an object model (scenario, step, ...) o Output in JSON format o REST API allows you to run any currently implemented function.
As an analyst, I can check how many steps the entire scenario (including sub-scenarios) contains to assess how complicated it is | 15 | 3 | 1 | o Empty scenario -> 0 steps o Number of scenario steps = Number of scenario steps + number of steps in all its direct and indirect sub-scenarios
As an analyst, I can check how many steps contain keywords to find out how many conditional decisions are in the scenario | 12 | 4 | 1 | o Each step in the structure starting with keywords increments the result by one o A scenario without steps starting with keywords yields a result of zero
As an analyst, I can see which steps do not start with the actor performing the action in order to correct this type of error | 10 | 4 | 1 | o For a scenario where all steps start with the actor name (keywords are ignored) the result is an empty list o In the event that any of the steps (at any level of depth) does not start with an actor (omitting keywords), all such steps must be returned as a list
As an analyst, I can download the scenario as a text with step numbers for inclusion in the documentation | 10 | 5 | 1.5 | o Each subsequent step on a given level is incremented by one number, starting with one and ending with a period (e.g. 1. 2. ...) o Numbers on successive levels of nesting are created by copying the number of the "parent" and assigning the numbering at a given level (eg 4.3.).
As an analyst, I can obtain a scenario containing only sub-scenarios up to a certain level to present a simplified version of the requirements | 10 | 5 | 1 | o The input contains the scenario structure and the level number o For level = 1, only the top-level scenario is returned o For levels> 1, scenarios up to and including the level are returned (e.g. level = 2 means the scenario at the highest level and its direct sub-scenarios)
As a user, I can utilise the application via the user interface |  | 11 |  | To be negotiated later

## Sprint #1 Backlog
Sprint Goal: | Build a first working REST version of ScenarioQualityChecker that accepts scenarios in JSON format, converts them into an object model, and provides basic quality-checking functions such as counting scenario steps, detecting decision-keyword steps, and identifying steps that do not start with an actor.
Product Backlog Item | Tasks | Labour intensity
As a developer of analyst tools, I can use the available functions remotely via REST to be able to integrate the tool with my other applications |  | 6
| Define JSON input/output structure and object model | 1
| Implement REST endpoint and service connection | 3
| Test API with sample JSON/Postman | 1
| Fix integration issues and document example request/response | 1
As an analyst, I can check how many steps the entire scenario (including sub-scenarios) contains to assess how complicated it is |  | 3
| Implement recursive step counting logic | 1
| Connect counting function to REST API response | 1
| Test empty, simple, and nested scenarios | 1
As an analyst, I can check how many steps contain keywords to find out how many conditional decisions are in the scenario |  | 4
| Define supported keywords and detection rules | 1
| Implement recursive keyword-step counting | 2
| Connect result to REST API and test examples | 1
As an analyst, I can see which steps do not start with the actor performing the action in order to correct this type of error |  | 4
| Define actor/keyword validation rules | 1
| Implement recursive invalid-step detection | 2
| Return invalid steps in JSON and test examples | 1
As an analyst, I can download the scenario as a text with step numbers for inclusion in the documentation |  | 5
| Define numbering format for normal and nested steps | 1
| Implement numbered text generation | 2
| Add REST endpoint and test downloadable/text response | 1
| Fix formatting and update README example | 1
As an analyst, I can obtain a scenario containing only sub-scenarios up to a certain level to present a simplified version of the requirements |  | 5
| Define level-filtering rules | 1
| Implement recursive scenario filtering | 2
| Add API parameter/endpoint and validate incorrect levels | 1
| Test level 1, level 2, and deeper scenarios | 1
As a user, I can utilise the application via the user interface |  | 11
| Agree UI scope with Product Owner | 1
| Create simple UI for entering scenario JSON and choosing function | 4
| Connect UI with REST API and display results | 2
| Add basic error handling and usability improvements | 2
| Manual UI testing and fixes | 2